## Task Tracker
PROJECT TASK TRACKER
DOCUMENT CONTROL
Project Name |  |  |  | Project Manager |  |  | Document ID | PMO-TT-001 | Version | 1.0 | Last Updated
TASK SUMMARY
TOTAL TASKS |  | COMPLETE |  | IN PROGRESS |  | NOT STARTED |  | ON HOLD |  | % DONE |  | HIGH PRIORITY
Task ID | WBS | Phase / Workstream | Task Name | Assigned To | Priority | Status | Planned Start | Planned End | Actual Start | Actual End | % Complete | Dependencies | Deliverable / Output | Remarks
T-001 | 1.1 | Phase 1 — Initiation | Project kick-off meeting conducted | Project Coordinator | HIGH | COMPLETE | 02/01/25 | 02/01/25 | 02/01/25 | 02/01/25 | 100% | — | Meeting Minutes — Kick-Off Meeting | Completed on schedule
T-002 | 1.2 | Phase 1 — Initiation | Letter of Award (LOA) received | Project Coordinator | HIGH | COMPLETE | 03/01/25 | 03/01/25 | 03/01/25 | 03/01/25 | 100% | T-001 | Letter of Award — Signed copy filed | LOA received from client
T-003 | 1.3 | Phase 1 — Initiation | Project Charter drafted and approved | Project Coordinator | HIGH | COMPLETE | 06/01/25 | 08/01/25 | 06/01/25 | 08/01/25 | 100% | T-002 | Project Charter v1.0 — Approved | Approved by PM
T-004 | 1.4 | Phase 1 — Initiation | Stakeholder register created | Project Coordinator | MEDIUM | COMPLETE | 09/01/25 | 10/01/25 | 09/01/25 | 10/01/25 | 100% | T-003 | Stakeholder Register v1.0
T-005 | 1.5 | Phase 1 — Initiation | Communication plan established | Project Coordinator | MEDIUM | COMPLETE | 13/01/25 | 14/01/25 | 13/01/25 | 14/01/25 | 100% | T-004 | Communication Plan v1.0
T-006 | 2.1 | Phase 2 — Planning | BRS sessions conducted with client | Business Analyst | HIGH | COMPLETE | 16/01/25 | 17/01/25 | 16/01/25 | 17/01/25 | 100% | T-005 | BRS Session Notes and Attendance Record | 2 sessions held
T-007 | 2.2 | Phase 2 — Planning | BRS document drafted and signed off | Business Analyst | HIGH | COMPLETE | 20/01/25 | 22/01/25 | 20/01/25 | 22/01/25 | 100% | T-006 | Business Requirements Spec (BRS) v1.0 — Signed | Client signed off 22 Jan
T-008 | 2.3 | Phase 2 — Planning | SRS drafted and approved | Business Analyst | HIGH | COMPLETE | 23/01/25 | 30/01/25 | 23/01/25 | 30/01/25 | 100% | T-007 | System Requirements Spec (SRS) v1.0 — Approved
T-009 | 2.4 | Phase 2 — Planning | Master project schedule developed and baselined | Project Coordinator | HIGH | COMPLETE | 29/01/25 | 30/01/25 | 29/01/25 | 30/01/25 | 100% | T-008 | Master Project Schedule — Baselined | Baseline locked 30 Jan
T-010 | 2.5 | Phase 2 — Planning | Risk register established | Project Coordinator | MEDIUM | COMPLETE | 31/01/25 | 03/02/25 | 31/01/25 | 03/02/25 | 100% | T-009 | Risk Register v1.0
T-011 | 3.1 | Phase 3 — Development | Portal architecture design | System Developer | HIGH | COMPLETE | 05/02/25 | 11/02/25 | 05/02/25 | 11/02/25 | 100% | T-010 | Portal Architecture Design Document
T-012 | 3.2 | Phase 3 — Development | User Management module development | System Developer | HIGH | COMPLETE | 12/02/25 | 25/02/25 | 12/02/25 | 25/02/25 | 100% | T-011 | User Management Module — Build Complete
T-013 | 3.3 | Phase 3 — Development | Portal module development | System Developer | HIGH | COMPLETE | 05/02/25 | 18/02/25 | 05/02/25 | 18/02/25 | 100% | T-011 | Portal Module — Build Complete | SS with T-012
T-014 | 3.4 | Phase 3 — Development | Data extraction from legacy system | Business Analyst | HIGH | COMPLETE | 05/02/25 | 11/02/25 | 05/02/25 | 11/02/25 | 100% | T-010 | Data Extraction Report
T-015 | 3.5 | Phase 3 — Development | Data cleansing and validation scripts | Business Analyst | HIGH | COMPLETE | 12/02/25 | 18/02/25 | 12/02/25 | 18/02/25 | 100% | T-014 | Data Cleansing and Validation Report
T-016 | 3.6 | Phase 3 — Development | Data migration dry run | Business Analyst | HIGH | IN PROGRESS | 19/02/25 | 21/02/25 | 19/02/25 |  | 60% | T-015 | Data Migration Dry Run Report | Verification in progress
T-017 | 3.7 | Phase 3 — Development | Data migration sign-off | Project Coordinator | HIGH | NOT STARTED | 21/02/25 | 21/02/25 |  |  | 0% | T-016 | Data Migration Sign-Off Form — Signed | Pending dry run completion
T-018 | 3.8 | Phase 3 — Development | Integration test environment setup | System Developer | MEDIUM | COMPLETE | 05/02/25 | 07/02/25 | 05/02/25 | 07/02/25 | 100% | T-010 | Integration Test Environment Setup Confirmation
T-019 | 3.9 | Phase 3 — Development | Integration testing Phase 1 | QA Tester | HIGH | COMPLETE | 10/02/25 | 18/02/25 | 10/02/25 | 18/02/25 | 100% | T-018 | Integration Test Report — Phase 1
T-020 | 3.10 | Phase 3 — Development | Integration testing Phase 2 | QA Tester | HIGH | COMPLETE | 19/02/25 | 27/02/25 | 19/02/25 | 27/02/25 | 100% | T-019 | Integration Test Report — Phase 2
T-021 | 3.11 | Phase 3 — Development | Integration sign-off | Project Coordinator | HIGH | COMPLETE | 28/02/25 | 03/03/25 | 28/02/25 | 03/03/25 | 100% | T-020 | Integration Sign-Off Form — Signed
T-022 | 3.12 | Phase 3 — Development | Server provisioning | Project Coordinator | MEDIUM | COMPLETE | 05/02/25 | 11/02/25 | 05/02/25 | 11/02/25 | 100% | T-010 | Server Provisioning Confirmation
T-023 | 3.13 | Phase 3 — Development | Environment configuration | Project Coordinator | MEDIUM | COMPLETE | 12/02/25 | 18/02/25 | 12/02/25 | 18/02/25 | 100% | T-022 | Environment Configuration Record
T-024 | 3.14 | Phase 3 — Development | Deployment checklist prepared | Project Coordinator | MEDIUM | COMPLETE | 19/02/25 | 21/02/25 | 19/02/25 | 21/02/25 | 100% | T-023 | Deployment Checklist v1.0
T-025 | 3.15 | Phase 3 — Development | Deployment readiness confirmed | Project Coordinator | MEDIUM | IN PROGRESS | 24/02/25 | 25/02/25 | 24/02/25 |  | 50% | T-024 | Deployment Readiness Confirmation
T-026 | 4.1 | Phase 4 — Testing | UAT plan prepared and distributed to client | Project Coordinator | HIGH | NOT STARTED | 07/03/25 | 10/03/25 |  |  | 0% | T-025 | UAT Test Plan v1.0
T-027 | 4.2 | Phase 4 — Testing | UAT conducted with client stakeholders | QA Tester | HIGH | NOT STARTED | 11/03/25 | 19/03/25 |  |  | 0% | T-026 | UAT Test Execution Report
T-028 | 4.3 | Phase 4 — Testing | UAT defects logged and resolved | System Developer | HIGH | NOT STARTED | 20/03/25 | 26/03/25 |  |  | 0% | T-027 | UAT Defect Log and Resolution Record
T-029 | 4.4 | Phase 4 — Testing | UAT sign-off by client | Project Coordinator | HIGH | NOT STARTED | 26/03/25 | 26/03/25 |  |  | 0% | T-028 | UAT Sign-Off Form — Signed | Milestone
T-030 | 4.5 | Phase 4 — Testing | FAT conducted with client stakeholders | QA Tester | HIGH | NOT STARTED | 27/03/25 | 02/04/25 |  |  | 0% | T-029 | FAT Test Execution Report
T-031 | 4.6 | Phase 4 — Testing | FAT defects logged and resolved | System Developer | HIGH | NOT STARTED | 03/04/25 | 07/04/25 |  |  | 0% | T-030 | FAT Defect Log and Resolution Record
T-032 | 4.7 | Phase 4 — Testing | FAT sign-off by client | Project Coordinator | HIGH | NOT STARTED | 07/04/25 | 07/04/25 |  |  | 0% | T-031 | FAT Sign-Off Form — Signed | Milestone
T-033 | 4.8 | Phase 4 — Testing | Go-Live readiness checklist completed | Project Coordinator | HIGH | NOT STARTED | 08/04/25 | 09/04/25 |  |  | 0% | T-032 | Go-Live Readiness Checklist — Completed
T-034 | 5.1 | Phase 5 — Close-Out | Go-Live deployment executed | Project Coordinator | HIGH | NOT STARTED | 10/04/25 | 10/04/25 |  |  | 0% | T-033 | Go-Live Deployment Confirmation | Milestone
T-035 | 5.2 | Phase 5 — Close-Out | Post-deployment monitoring | Project Coordinator | HIGH | NOT STARTED | 11/04/25 | 17/04/25 |  |  | 0% | T-034 | Post-Deployment Monitoring Report
T-036 | 5.3 | Phase 5 — Close-Out | Handover documentation prepared | Project Coordinator | MEDIUM | NOT STARTED | 11/04/25 | 15/04/25 |  |  | 0% | T-034 | Handover Documentation Package
T-037 | 5.4 | Phase 5 — Close-Out | Client training conducted | Business Analyst | MEDIUM | NOT STARTED | 16/04/25 | 17/04/25 |  |  | 0% | T-036 | Training Completion Record and Attendance
T-038 | 5.5 | Phase 5 — Close-Out | Project close-out report submitted | Project Coordinator | HIGH | NOT STARTED | 18/04/25 | 21/04/25 |  |  | 0% | T-037 | Project Close-Out Report v1.0
T-039 | 5.6 | Phase 5 — Close-Out | Project formally closed | Project Coordinator | HIGH | NOT STARTED | 22/04/25 | 22/04/25 |  |  | 0% | T-038 | Project Closure Sign-Off — Formally Closed | Milestone

## Instructions
HOW TO USE THIS TEMPLATE
DOCUMENT CONTROL
Fill in Project Name, Project Manager, Document ID (e.g. PMO-TT-001), Version, and Last Updated date. Increment version each time the tracker is significantly revised.
TASK SUMMARY CARDS
Auto-calculated from your task list. No manual input needed. Total tasks, complete, in progress, not started, on hold, % done, and high priority count all update automatically when you update task statuses.
TASK ID
Use format T-001, T-002, T-003. Sequential and consistent. Used for cross-referencing in Dependencies column, RAID log, and meeting minutes.
WBS
Work Breakdown Structure code tied to the approved project scope. Format: Phase.Task (e.g. 1.1, 2.3, 3.10). Should match WBS codes in your MS Project schedule and project scope document.
PHASE / WORKSTREAM
Group tasks by project phase (Phase 1 — Initiation, Phase 2 — Planning, etc.). Allows filtering and phase-level progress tracking.
ASSIGNED TO
Enter the name of the person responsible for completing the task. Not a team or department — a named individual. Ownership must be unambiguous.
PRIORITY
HIGH = directly impacts milestone or critical path, must complete on time. MEDIUM = important but has scheduling flexibility. LOW = can be deferred if higher priority tasks need attention.
STATUS
COMPLETE = done and verified. IN PROGRESS = actively being worked on. NOT STARTED = not yet begun. ON HOLD = paused, reason in Remarks. OVERDUE = planned end date passed and task not complete.
PLANNED START / END
Enter from your MS Project baseline schedule. Do not change once set. These are your reference dates for variance tracking.
ACTUAL START / END
Fill in as tasks begin and complete. Leave blank if not yet started. Variance between planned and actual is your schedule slippage indicator.
% COMPLETE
Enter as a decimal (0.0 to 1.0). The KPI card reads this automatically. Be accurate — 0.9 means 90% of the work is done, not 90% of time elapsed.
DEPENDENCIES
Enter the Task ID that must finish before this task can start. Use T-XXX format. For parallel tasks note SS (Start-to-Start). Mirrors predecessor logic in MS Project.
DELIVERABLE / OUTPUT
The formal document or artefact produced when this task is complete. Examples: BRS v1.0 — Signed, UAT Sign-Off Form, Deployment Checklist. This is what the client or auditor will look for as evidence of task completion.
REMARKS
Brief notes on delays, blockers, decisions, or escalations. One to two lines maximum. This forms your informal audit trail between formal status reports.
STATUS AND PRIORITY LEGEND
COMPLETE | Task finished and verified. Actual end date recorded.
IN PROGRESS | Task actively being worked on. % Complete should reflect actual progress.
NOT STARTED | Task not yet begun. Planned start date is in the future.
ON HOLD | Task paused. Reason must be noted in Remarks. Escalate if hold exceeds 1 week.
OVERDUE | Planned end date has passed and task is not complete. Requires immediate escalation.
HIGH | Priority: directly impacts milestone or critical path. Must complete on time.
MEDIUM | Priority: important but has some scheduling flexibility.
LOW | Priority: can be deferred if high priority tasks require attention.